## Frame
Master Deliverables List
Frame Stage
Item No. | Deliverable Description | Status | Status | Discipline | Notes
1 | Process Description / PFD | Prelim | IFR | Process
2 | Process Design Basis | Prelim |  | Process | Pressures/temps/fluids/utilities
3 | General Arrangement | Prelim |  | C/S | Used for TIC basis
4 | Equipment List | Prelim |  | Mech | Rough sizes / quantities to aid in TIC
5 | TIC Estimate | IFA | FYU | Project | +/- 50% Estimate
6 | Milestone identification | Prelim |  | Project | Commissioning dates; perceived long lead equipment
Issued for Information

## Screen
Master Deliverables List
Screen Stage
Item No. | Deliverable Description | Status | Status | Discipline | Notes
1 | Process Design Basis | Prelim | IFR | Process | Including utillity and chemical requirements
2 | Process Flow Diagram | IFA | IFD | Process
3 | Heat and Material Balance | IFA | IFD | Process
4 | Preliminary or Red-line existing P&ID's | Prelim | IFR | Process
5 | Line Sizing/Hydraulics | Prelim |  | Process | To extent required to support P&ID development/revisions
6 | Site Topographical Survey Scope of Work | FYU |  | C/S
7 | Soils Report and/or Soils Boring Location Plan Scope of Work | FYU |  | C/S
8 | Civil/Structural conceptual design | Prelim | IFR | C/S | Including building requirements; approx sizes, etc
9 | Long lead or unique civil structural specifications (buildings, etc.) | Prelim | IFR | C/S | As appropriate to support execution plan and/or estimate
10 | Materials of Construction Diagram | Prelim | IFR | Mech | As needed
11 | Equipment List | Prelim | IFR | Process | Process data sheet not necessary, but some preliminary sizing basis needs to be included in equipment list. All equipment needs to be included if a factored TIC is required
12 | Piping Line List | Prelim | IFR | Mech | As required to support TIC; will depend on level of P&ID development
13 | Piping Tie-in List | Prelim | IFR | Mech
14 | Long lead or unique equipment specifications | Prelim | IFR | Mech | As appropriate to support execution plan and/or estimate
15 | Area classification | Prelim | IFR | Elec | As appropriate to support execution plan and/or estimate
16 | Electrical one-line diagrams | Prelim | IFR | Elec
17 | Long lead electrical specifications | Prelim | IFR | Elec | As appropriate to support execution plan and/or estimate
18 | System block diagram | Prelim | IFR | I&C | As appropriate to support execution plan and/or estimate
19 | Long lead I&C specifications | Prelim | IFR | I&C | As appropriate to support execution plan and/or estimate
20 | Conceptual plot plan | Prelim | IFR | Piping | Can be collaborative effort between structural and piping. Siting and code issues need to be assigned as appropriate; document needs to be squad checked
21 | Piping Plan/One-Line and/or Preliminary Model w/BOM | Prelim |  | Piping | As appropriate to support execution plan and/or TIC estimate
22 | Options Analysis and Selection | IFR | IFA | Project
23 | Project Basis of Design - all disciplines | IFR | IFA | Project | Includes ISBL/OSBL definition; spec list; major crane requirements; constructability; engineering, procurement, construction plan
24 | Cost Estimate for Define Engineering | IFA | FYU | Project
25 | Total Installed Cost Estimate | IFA | FYU | Project | Accuracy -30/+30%; includes basis of estimate document
26 | Project milestone schedule | IFA | FYU | Project | Details for Screen Engineering included

## Refine
Master Deliverables List
Refine Stage
Item No. | Deliverable Description | Status | Status | Status | Discipline | Notes
1 | Process Design Basis |  | IFA | IFD | Process | Including utillity and chemical requirements
2 | Process, Utility and Auxiliary P&ID's |  | IFA | IFD | Process
3 | Demolition P&ID's (mark-ups of existing P&ID's) |  | IFA | IFD | Process | If required
4 | Design Review (Pre-HAZOP) | Prelim |  |  | Process
5 | Equipment Data Sheets |  | IFA | IFD | Process
6 | Process Instrument Datasheets (In-line only) |  | IFA | IFD | Process | Process condition input to I&C datasheets
7 | Relief reports | Prelim |  |  | Process | including relief valve datasheets and relief load summary
8 | Soils Report and/or Soils Boring Location Plan Scope of Work | FYU |  |  | C/S | If not completed in previous phase
9 | Site Topographical Survey Scope of Work | FYU |  |  | C/S | If not completed in previous phase
10 | Site Preparation Requirements | IFR |  |  | C/S
10.5 | Civil Site & Drainage Drws | IFR | IFA |  | C/S
11 | Equipment Location Plans/Elevations | IFR | IFA |  | C/S
12 | Building Specifications and General Arrangements (Control Rooms, MCC, etc.) | IFR | IFA |  | C/S | for non-equipment items
13 | Foundation Sketches | IFR |  |  | C/S | Prelim BOM as necessary for TIC
14 | Structural Steel Sketches | IFR |  |  | C/S | Prelim BOM as necessary for TIC
15 | Underground Piping Systems: Oily Water, Storm Water (sketches) | IFR |  |  | C/S | underground, non-pressurized
16 | GA's for Equipment Supported Ladders and Platforms |  | IFA | IFB | C/S | to go with mechanical vessel drawings
17 | Materials of Construction Diagram |  | IFA | IFD | Mech | If required
18 | Vessel Design Drawings |  | IFA | IFB | Mech
19 | Long Lead Equipment Specification | IFA | IFB | IFP | Mech
20 | Long Lead Equipment Bid Tabs and Technical Evaluation |  | IFA |  | Mech
21 | Balance of Equipment Specifications | IFR |  |  | Mech | for budgetary quotes only
22 | Piping Stress Analysis | Prelim |  |  | Mech | for critical lines
23 | Piping Line List |  | IFA | IFD | Mech | including paint and insulation schedule; hydro & heat treat requirements
24 | Tie-in List |  | IFA | IFD | Mech | Collaborative effort between mechanical and piping.
25 | Equipment List | IFR |  |  | Mech
26 | Specialty Item List | IFR |  |  | Mech
27 | 30% Model Review | IFR |  |  | Piping
28 | Piping Plan/One-Line and/or Preliminary Model w/BOM | IFR |  |  | Piping | As appropriate to support execution plan and/or TIC estimate
29 | Isometric Sketches for High Temperature, Alloy and Large (>24") Piping | IFR |  |  | Piping
30 | System Modeling - (Arc Flash, Relay Coordination, etc.) | IFR |  |  | Elec
31 | Electrical One-Line |  | IFA | IFD | Elec
32 | Electrical Area Classification |  | IFA | IFD | Elec
33 | Electrical Load List |  | IFA | IFD | Elec
34 | Electrical Data Sheets |  | IFA | IFB | Elec
35 | Electrical/MCC Building Layout | IFA | IFB | IFD | Elec
36 | Cable tray, underground conduit and fiber optic routing - preliminary | IFR |  |  | Elec
37 | Long Lead Electrical Equipment Specifications | IFA | IFB | IFP | Elec
38 | Long Lead Electrical Equipment Bid Tab and Technical Evaluation | IFA |  |  | Elec
39 | Instrument Index and Pricing Basis |  | IFA | IFD | I&C
40 | Control system cabinet design |  | IFA | IFB | I&C
41 | DCS Interface/Requirements and Pricing |  | IFA | IFB | I&C
42 | Instrument datasheets (in-line, long lead, specialty) |  | IFA | IFB | I&C
43 | Long Lead I&C Specifications | IFA | IFB | IFP | I&C | RIE Buildings, cabinets, control valves, instruments, etc.
44 | Long Lead I&C Bid Tabs and Technical Evaluations |  | IFA |  | I&C
45 | SIL and Layer of Protection Analysis | Prelim |  |  | I&C
46 | Safety Instrumented Systems Review | Prelim |  |  | I&C
47 | Control building layout | IFA | IFB | IFD | I&C
48 | Control system philosophy & narrative | Prelim |  |  | I&C
49 | Project Equipment Inspection Requirements/Plan | IFR | IFA |  | Procurement
50 | Long Lead Equipment Commercial Bid Tab and Purchase Recommendation |  | IFA |  | Procurement
51 | Long Lead Electrical Equipment Commercial Bid Tab and Purchase Recommendation |  | IFA |  | Procurement
52 | Long Lead I&C Commercial Bid Tab and Purchase Recommendation |  | IFA |  | Procurement
53 | Initial Value Engineering and Constructability Assessment | IFR | IFA |  | PM
54 | Definitive Cost Estimate with ISBL and OSBL Components |  | IFA | FYU | PM | Accuracy -10/+15%
55 | Execution Plan for Detail Design, Procurement and Construction |  | IFA | FYU | PM
56 | Major crane requirements and Preliminary Rigging and Lifting Plans | IFR | IFA |  | PM
57 | Define stage ISBL and OSBL Consolidated EPC Project Schedule |  | IFA | FYU | PM
58 | Basis of Design - all disciplines |  | IFA | IFD | PM | Input from all disciplines. Includes ISBL/OSBL definition; spec list; major crane requirements; constructability; engineering, procurement, construction plan

## Implement
Master Deliverables List
Implement Stage
Item No. | Deliverable Description | Status | Status | Status | Discipline | Notes
1 | Process, Utility and Auxiliary P&ID's |  |  | IFC | Process
2 | Demolition P&ID's (mark-ups of existing P&ID's) |  |  | IFC | Process
3 | HAZOP Review |  |  | Final | Process
4 | Relief reports |  |  | Final | Process | including relief valve datasheets and relief load summary
5 | Relief Valve Datasheets |  | IFA | IFP | Process
6 | Flare Study Addendums |  | IFA | Final | Process
7 | MOC Log |  | IFA | Final | Process | to track changes after HAZOP
8 | Process Flow Diagram | Project Bk Only |  |  | Process | (IFD) Include in final project book, but not a detailed deliverable
9 | Heat and Material Balance | Project Bk Only |  |  | Process | (IFD) Include in final project book, but not a detailed deliverable
10 | Equipment Data Sheets | Project Bk Only |  |  | Process | (IFD) Include in final project book, but not a detailed deliverable
11 | Process Instrument Datasheets (In-line only) | Project Bk Only |  |  | Process | (IFD) Include in final project book, but not a detailed deliverable
12 | Process Design Basis | Project Bk Only |  |  | Process | (IFD) Include in final project book, but not a detailed deliverable
13 | Site Preparation Requirements (grading plans/sections) |  | IFA | IFC | C/S
14 | Equipment Location Plans/Elevations |  |  | IFC | C/S
15 | Building Specifications and General Arrangements (Control Rooms, MCC, etc.) |  | IFB |  | C/S | for non-equipment items
16 | Concrete Location Plan |  | IFA | IFC | C/S
17 | Concrete Detail Drawings |  | IFA | IFC | C/S
18 | Paving Plan |  | IFA | IFC | C/S
19 | Structural Steel Location Plan |  | IFA | IFC | C/S
20 | Structural Steel Drawings |  | IFA | IFC | C/S
21 | Fire Protection Coating Drawings |  | IFA | IFC | C/S | fireproofing
22 | Civil/Structural General Notes |  | IFA | IFC | C/S
23 | Drilled Pier or Footing Schedule and Details |  | IFA | IFC | C/S
24 | Anchor Rod Schedule and Details |  | IFA | IFC | C/S
25 | Underground Piping Systems: Oily Water, Storm Water Drawings |  | IFA | IFC | C/S | underground, non-pressurized
26 | Soils Report and/or Soils Boring Location Plan Scope of Work | Project Bk Only |  |  | C/S | (IFU) Include in final project book, but not a detailed deliverable
27 | Site Topographical Survey Scope of Work | Project Bk Only |  |  | C/S | (IFU) Include in final project book, but not a detailed deliverable
28 | GA's for Equipment Supported Ladders and Platforms | Project Bk Only |  |  | C/S | (IFB) Include in final project book, but not a detailed deliverable
29 | Vessel Design Drawings |  | IFD |  | Mech | included in IFP technical specification
30 | Equipment Specifications | IFA | IFB | IFP | Mech
31 | Equipment Bid Tab and Technical Evaluation |  | IFA |  | Mech
32 | Piping Stress Analysis |  | IFA | Final | Mech | if these are issued
33 | Engineered Pipe Supports |  | IFA | IFP | Mech | springs/snubbers (non-standard and non-MPS supports)
34 | Piping Line List |  |  | IFC | Mech
35 | Tie-in List |  |  | IFC | Mech | Collaborative effort between mechanical and piping.
36 | Equipment List |  | IFA | FInal | Mech
37 | Specialty Item List |  | IFA | FInal | Mech
38 | Materials of Construction Diagram | Project Bk Only |  |  | Mech | (IFD) Include in final project book, but not a detailed deliverable
39 | 60% Model Review | IFR |  |  | Piping | Navis Model
40 | 90% Model Review |  | IFA |  | Piping | Navis Model
41 | Piping BOM |  | IFA | IFP | Piping
42 | Isometrics |  | IFA | IFC | Piping | includes Fire Water/Potable Piping
43 | Miscellanous Pipe Supports |  | IFA | IFC | Piping
44 | Piping Plans and Elevations |  | IFA | IFC | Piping
45 | System Modeling - (Arc Flash, Relay Coordination, etc.) |  | IFA | IFRecord | Elec
46 | Electrical One-Line |  | IFA | IFC | Elec | if not IFA'd in define
47 | Electrical Area Classification |  | IFA | IFC | Elec | if not IFA'd in define
48 | Electrical Load List |  | IFA | IFC | Elec | if not IFA'd in define
49 | Electrical Data Sheets |  |  | IFP | Elec
50 | Cable tray detail and plan drawings |  | IFA | IFC | Elec
51 | Power plan drawings |  | IFA | IFC | Elec
52 | Ductbank details and plan drawings |  | IFA | IFC | Elec
53 | Electrical Cable Schedule |  | IFA | IFC | Elec | Balance of work not covered in Define phase
54 | Grounding Plan |  | IFA | IFC | Elec
55 | Lighting Plan |  | IFA | IFC | Elec
56 | Demo wiring and plan drawings |  | IFA | IFC | Elec
57 | Motor Schematics |  | IFA | IFC | Elec
58 | Wiring Diagrams |  | IFA | IFC | Elec
59 | Electrical BOM |  | IFA | IFP | Elec
60 | Installation Details | IFR |  |  | Elec | Issue new or project approval details as IFA/IFR
61 | Instrument Index |  | IFA | IFC | I&C | if not IFA'd in define
62 | Instrument datasheets | IFA | IFB | IFP | I&C | Balance of instruments not purchased in Define Phase
63 | Instrument Cable Schedule |  | IFA | IFC | I&C
64 | Field Junction Box layouts |  | IFA | IFC | I&C
65 | Marshalling panel layouts |  | IFA | IFC | I&C
66 | Control system cabinet design |  | IFA | IFC | I&C | IFP if we are purchasing
67 | Loop Diagrams |  | IFA | IFC | I&C
68 | Wiring Diagrams |  | IFA | IFC | I&C
69 | Instrument plan drawings |  | IFA | IFC | I&C
70 | Demo wiring and plan drawings |  | IFA | IFC | I&C
71 | Installation Details | IFR |  |  | I&C | Issue new or project approval details as IFA/IFR
72 | Instrument Installation BOM |  | IFA | IFP | I&C
73 | FAT/SAT Procedures and Execution |  | IFA | IFRecord | I&C
74 | PLC/HMI Programming |  | IFA | IFRecord | I&C
75 | Cause and Effect Matrix |  | IFA | IFC | I&C
76 | Control system philosophy & narrative |  | IFA | IFC | I&C | Balance of work not covered in Define phase
77 | SIL Calculations |  | IFA | IFRecord | I&C
78 | Mechanical Equipment Commercial Bid Tab and Purchase Recommendation |  | IFA |  | Procurement
79 | Electrical Equipment Commercial Bid Tab and Purchase Recommendation |  | IFA |  | Procurement
80 | I&C Commercial Bid Tab and Purchase Recommendation |  | IFA |  | Procurement
81 | Execution Plan for Detail Design, Procurement and Construction |  | IFA | FYU | PM | If not completed in define
82 | Detail project schedule |  | IFA | FYU | PM | Updated/refined from define phase
83 | Basis of Design - all disciplines |  |  | Final | PM | updated from define phase as required